## Task List
Brain Tumor Classification — ML Pipeline Task List
BMEN 207 Honors Project — Bhargav Ashwin & Dhir Parekh
# | Pipeline Stage | Task Description | Status | Owner | Notes
1 | Data Collection & Preparation | Set up project folder structure (brain tumor analysis directory) | Complete | Dhir / Bhargav
2 | Data Collection & Preparation | Set up Python virtual environment and install all required libraries | Complete | Dhir / Bhargav
3 | Data Collection & Preparation | Download Kaggle MRI dataset (7,000+ images across 4 classes) | Complete | Bhargav
4 | Preprocessing | Explore and audit the dataset (class distribution, image sizes, formats) | Complete | Bhargav
5 | Preprocessing | Preprocess images (resize, normalize, grayscale/RGB standardization) | Complete | Bhargav
6 | Preprocessing | Apply data augmentation (flips, rotations, contrast via Albumentations) | Complete | Bhargav
7 | Preprocessing | Split dataset into training (1,400/class) and testing (400/class) sets | Complete | Bhargav
8 | Preprocessing | Organize test set into 4 batches of 100 images per class | Complete | Bhargav
9 | Preprocessing | Build PyTorch DataLoader pipeline (custom Dataset class, transforms) | Complete | Dhir
10 | Model Development | Research and select CNN architecture (ResNet/EfficientNet as baseline) | Complete | Dhir
11 | Model Development | Implement model architecture with transfer learning in PyTorch | Complete | Dhir
12 | Model Development | Configure training parameters (learning rate, optimizer, loss, epochs) | Complete | Dhir
13 | Training Loop | Train the model on training set with GPU (Google Colab) | Complete | Dhir
14 | Evaluation | Evaluate model on 4 test batches and track accuracy consistency | Complete | Dhir
15 | Evaluation | Generate confusion matrix, precision, recall, and F1 scores | Complete | Dhir
16 | Evaluation | Integrate Grad-CAM via pytorch-grad-cam for explainability heatmaps | Complete | Dhir
17 | Testing & Finalization | Validate model on Cancer Imaging Archive samples for generalizability | Complete | Dhir / Bhargav
18 | Testing & Finalization | Visualize results: sample predictions with Grad-CAM overlays per class | Complete | Bhargav
19 | Testing & Finalization | Compare performance against Kaggle baseline benchmark | Complete | Dhir
20 | Testing & Finalization | Compile final report with methodology, results, visualizations, and discussion | Complete | Dhir / Bhargav
Stage Legend:
Data Collection & Preparation
Preprocessing
Model Development
Training Loop
Evaluation
Testing & Finalization

## Risk Register
Brain Tumor Classification — Risk Register
BMEN 207 Honors Project — Bhargav Ashwin & Dhir Parekh
# | Risk | Description | Likelihood | Impact | Severity | Affected Tasks | Mitigation Strategy
1 | Model Overfitting | The CNN learns dataset-specific patterns from the Kaggle MRI set and fails to generalize to real-world clinical images. | High | High | Critical | Tasks 11, 13, 14, 17 | Apply data augmentation (Task 6), use dropout layers and early stopping in training (Task 13), and validate on Cancer Imaging Archive data (Task 17) to confirm generalizability beyond the curated dataset.
2 | Class Imbalance | Unequal image counts across glioma, meningioma, no_tumor, and pituitary classes causes the model to favor majority classes and under-detect rare types. | Medium | High | High | Tasks 4, 7, 15 | Audit class distribution during dataset exploration (Task 4), apply stratified splitting (Task 7), and use per-class F1/precision/recall metrics rather than overall accuracy (Task 15) to detect and surface any bias.
3 | Grad-CAM Clinically Irrelevant Highlights | Explainability heatmaps may focus on image artifacts, scan borders, or noise rather than actual tumor anatomy, undermining clinical trust and the core value proposition of the project. | Medium | High | High | Tasks 16, 18 | Visually inspect Grad-CAM overlays across all 4 tumor classes (Task 18) and cross-reference highlighted regions with known neuroanatomy. Flag and document any cases where activation maps appear clinically inconsistent.
4 | Insufficient Dataset Size | 1,400 training images per class may be too few for a robust CNN, leading to high variance between training and test batch accuracy scores. | Low | High | Medium | Tasks 3, 7, 13 | Supplement with Cancer Imaging Archive images if batch accuracy is inconsistent (Task 17). Use transfer learning from a pre-trained ImageNet model (Task 11) to reduce data requirements significantly.
5 | GPU Resource Constraints | Google Colab free-tier GPU sessions time out, which could interrupt long training runs and cause loss of model checkpoints. | Medium | Medium | Medium | Task 13 | Save model checkpoints to Google Drive after each epoch. Structure training in resumable phases and consider Colab Pro if free-tier limits are frequently hit.
Severity Legend:
Critical
High
Medium